## Slide 1: Update – SACSCOC Off-Site and On-Site Visits
Cheryl Gater, Director, SACSCOC Accreditation

## Slide 2: SACSCOC Review Calendar
November 5-8, 2013: Off-Site Review
  December/January – Focused Report due, UF’s response to off-site review committee report
Mid January 2014 (4-6 weeks prior to site visit): QEP Due

## Slide 3: SACSCOC Review Calendar
February 18-20, 2014: On-Site Review
  July 2014: UF’s Response to On-Site Committee report
December 5-9, 2014: SACSCOC Board of Trustees Review and final recommendations

## Slide 4: SACSCOC On-Site Review February 18-20, 2014
End of January, early February – We should have a general idea of meetings requested by the review committee.
  Be prepared for last minute requests – Especially Day 1
UF off-campus education site visits will occur typically Sunday or Monday before the official on-site review dates. Site visits TBD, but we should know a few weeks in advance.

## Slide 5: SACSCOC On-Site Review February 18-20, 2014
Day 1 – Tuesday, February 18 – Starts late morning
  Committee focuses on completing its review of all of the compliance issues stemming from standards marked “non-compliance” or “did not review” by the off-site review committee
  Committee conducts interviews and requests any necessary further documentation
  Be prepared for last minute requests that have to be completed quickly

## Slide 6: SACSCOC On-Site Review February 18-20, 2014
Day 2 – Wednesday, February 19
  Committee focuses on the QEP
    UF makes formal presentation of QEP
    Committee conducts QEP interviews
Day 3 – Thursday, February 20 – concludes by mid-morning
  Committee presents its findings to UF leadership at the Exit Conference